## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | ACTIVIDADES GENERALES | 1
2 | TRABAJOS PRELIMINARES | 1.1
3 | MOVILIZACION Y DESMOVILIZACION DE MAQUINARIAS Y EQUIPOS | 1.1.1 |  | FS6;FS7;FS58;FS43 | 2020-08-18 |  | 1d | mason |  | 16275 |  | 0
4 | PUENTE CONIN | 2
5 | OBRAS PRELIMINARES | 2.1
6 | CARTEL DE OBRA | 2.1.1 | 3FS |  | 2020-08-19 |  | 1d | painter |  | 450 |  | 0
7 | LIMPIEZA DEL TERRENO MANUAL | 2.1.2 | 3FS | FS8;FS38 | 2020-08-19 |  | 2d | team subcontractor |  | 5779.8 |  | 0
8 | ALMACEN Y GUARDIANIA | 2.1.3 | 7FS | FS9 | 2020-08-21 |  | 3d | mason |  | 1200 |  | 0
9 | TRAZO Y REPLANTEO INICIAL | 2.1.4 | 8FS |  | 2020-08-24 |  | 2d | team subcontractor |  | 988 |  | 0
10 | ENCAUZAMIENTO DEL CAUCE DEL RIO | 2.1.5 |  | FS12 | 2020-08-18 |  | 7d | carpenter |  | 11243.6 |  | 0
11 | SUBESTRUCTURA | 2.2
12 | EXCAVACION PARA ESTRIBOS EN TERRENO NORMAL CON MAQUINARIA | 2.2.1 | 10FS | FS13 | 2020-08-25 |  | 5d | team subcontractor[2.00 #8] |  | 5325.2 |  | 0
13 | RELLENO COMPACTADO CON MATERIAL PROPIO | 2.2.2 | 12FS | FS15 | 2020-08-30 |  | 6d | electrician |  | 4105.52 |  | 0
14 | ELIMINACION DE MATERIAL EXCEDENTE CON MAQUINARI, D=1.5 KM. | 2.2.3
15 | ENCOFRADO Y DESENCOFRADO DE ESTRIBO | 2.2.3.1 | 13FS | FS16 | 2020-09-05 |  | 7d | team subcontractor[2.00 #8] |  | 15108.88 |  | 0
16 | CONCRETO f'c=175 kg/cm2 + 30% PM. | 2.2.3.2 | 15FS | FS23;FS18 | 2020-09-12 |  | 10d | team subcontractor[2.00 #8] |  | 59414.72 |  | 0
17 | PUENTE PROVISIONAL | 2.3
18 | SUPERESTRUCTURA DE ROLLIZO (L=18.00 M.) | 2.3.1 | 16FS | FS19;FS20 | 2020-09-22 |  | 5d | team subcontractor[3.00 #8] |  | 4304.28 |  | 0
19 | CONSTRUSSION DE MADERAMEN | 2.3.2 | 18FS | FS21 | 2020-09-27 |  | 5d | electrician |  | 20411.64 |  | 0
20 | ALCAYATAS T-1 | 2.3.3 | 18FS |  | 2020-09-27 |  | 2d | team subcontractor[3.00 #8] |  | 2556.64 |  | 0
21 | ALCAYATAS T-2 | 2.3.4 | 19FS |  | 2020-10-02 |  | 2d | mason |  | 1384.8 |  | 0
22 | DEFENSA RIBEREÑA | 2.4
23 | EXCAVACION EN MATERIAL COMUN BAJO AGUA | 2.4.1 | 16FS | FS24 | 2020-09-22 |  | 3d | electrician |  | 2022.24 |  | 0
24 | PERFILADO PARA BASE DE ESTRUCTURA | 2.4.2 | 23FS | FS25 | 2020-09-25 |  | 3d | painter |  | 835.65 |  | 0
25 | RELLENO Y COMPACTADO PARA ESTRUCTURAS | 2.4.3 | 24FS | FS26 | 2020-09-28 |  | 3d | mason |  | 1278.72 |  | 0
26 | ELIMINACION DE MATERIAL EXCEDENTE A 100M. | 2.4.4 | 25FS | FS27;FS28;FS33 | 2020-10-01 |  | 1d | carpenter |  | 1229.56 |  | 0
27 | GEOTEXTIL NO TEJIDO TIPO I | 2.4.5 | 26FS |  | 2020-10-02 |  | 2d | mason |  | 260.46 |  | 0
28 | GAVIONES TIPO CAJA 5.0x1.0x2.0 | 2.4.6 | 26FS | FS29;FS30;FS31 | 2020-10-02 |  | 3d | electrician |  | 10008.6 |  | 0
29 | GAVIONES TIPO CAJA 5.0x1.0x1.5 | 2.4.7 | 28FS | FS40 | 2020-10-05 |  | 7d | carpenter |  | 23678.33 |  | 0
30 | GAVIONES TIPO CAJA 5.0x1.0x1.0 | 2.4.8 | 28FS |  | 2020-10-05 |  | 3d | mason |  | 5616.45 |  | 0
31 | GAVIONES TIPO COLCHON 5.0x2.0x0.30M. | 2.4.9 | 28FS |  | 2020-10-05 |  | 2d | mason |  | 3925.8 |  | 0
32 | ENROCADO DE PROTESSION (AGUAS ARRIBA) | 2.5
33 | EXTRASSION, SELESSIÓN Y ACOPIO DE ROCA | 2.5.1 | 26FS | FS34 | 2020-10-02 |  | 2d | mason |  | 274.8 |  | 0
34 | CARGUIO Y TRANSPORTE DE ROCA (D=1KM) | 2.5.2 | 33FS | FS35;FS36 | 2020-10-04 |  | 2d | carpenter |  | 375.6 |  | 0
35 | ACOMODADO DE ROCA EN LA UÑA | 2.5.3 | 34FS |  | 2020-10-06 |  | 1d | painter |  | 81.45 |  | 0
36 | ACOMODADO DE ROCA EN TALUD | 2.5.4 | 34FS |  | 2020-10-06 |  | 1d | plasterer |  | 244.13 |  | 0
37 | SEGURIDAD Y SALUD OCUPACIONAL | 2.6
38 | SEGURIDAD Y SALUD | 2.6.1 | 7FS |  | 2020-08-21 |  | 5d | electrician |  | 1000 |  | 0
39 | MITIGACION AMBIENTAL | 2.7
40 | MITIGACION DE IMPACTO AMBIENTAL | 2.7.1 | 29FS |  | 2020-10-12 |  | 1d | mason |  | 1000 |  | 0
41 | PUENTE CHACPAR | 3
42 | OBRAS PRELIMINARES | 3.1
43 | CARTEL DE OBRA | 3.1.1 | 3FS | FS44 | 2020-08-19 |  | 1d | plasterer |  | 450 |  | 0
44 | LIMPIEZA DEL TERRENO MANUAL | 3.1.2 | 43FS | FS45;FS53 | 2020-08-20 |  | 6d | mason |  | 2808 |  | 0
45 | ALMACEN Y GUARDIANIA | 3.1.3 | 44FS | FS47 | 2020-08-26 |  | 1d | mason |  | 1200 |  | 0
46 | REPARACION DE ESTRUCTURA | 3.2
47 | ELIMINACION DE ROLLIZOS Y TABLONES | 3.2.1 | 45FS | FS48 | 2020-08-27 |  | 1d | carpenter |  | 743.15 |  | 0
48 | SUPERESTRUCTURA DE ROLLIZO (L=11.80 M.) | 3.2.2 | 47FS | FS49;FS50;FS51 | 2020-08-28 |  | 1d | plasterer |  | 4124.28 |  | 0
49 | CONSTRUSSION DE MADERAMEN | 3.2.3 | 48FS | FS55 | 2020-08-29 |  | 24d | painter |  | 13582.28 |  | 0
50 | ALCAYATA T-1 | 3.2.4 | 48FS |  | 2020-08-29 |  | 4d | carpenter |  | 1719.12 |  | 0
51 | ALCAYATA T-2 | 3.2.5 | 48FS |  | 2020-08-29 |  | 2d | carpenter |  | 900.12 |  | 0
52 | SEGURIDAD Y SALUD OCUPACIONAL | 3.3
53 | SEGURIDAD Y SALUD | 3.3.1 | 44FS |  | 2020-08-26 |  | 5d | carpenter |  | 1000 |  | 0
54 | MITIGACION AMBIENTAL | 3.4
55 | MITIGACION DE IMPACTO AMBIENTAL | 3.4.1 | 49FS |  | 2020-09-22 |  | 1d | carpenter |  | 1000 |  | 0
56 | PUENTE LANCHAN | 4
57 | OBRAS PRELIMINARES | 4.1
58 | CARTEL DE OBRA | 4.1.1 | 3FS | FS59 | 2020-08-19 |  | 1d | mason |  | 450 |  | 0
59 | LIMPIEZA DEL TERRENO MANUAL | 4.1.2 | 58FS | FS60;FS68 | 2020-08-20 |  | 4d | mason |  | 1872 |  | 0
60 | ALMACEN Y GUARDIANIA | 4.1.3 | 59FS | FS62 | 2020-08-24 |  | 1d | painter |  | 1200 |  | 0
61 | REPARACION DE ESTRUCTURA | 4.2
62 | ELIMINACION DE ROLLIZOS Y TABLONES | 4.2.1 | 60FS | FS63 | 2020-08-25 |  | 1d | mason |  | 743.15 |  | 0
63 | SUPERESTRUCTURA DE ROLLIZO (L=6.80 M.) | 4.2.2 | 62FS | FS64;FS65;FS66 | 2020-08-26 |  | 1d | team subcontractor |  | 4004.28 |  | 0
64 | CONSTRUSSION DE MADERAMEN | 4.2.3 | 63FS | FS70 | 2020-08-27 |  | 18d | mason |  | 7625.16 |  | 0
65 | ALCAYATA T-1 | 4.2.4 | 63FS |  | 2020-08-27 |  | 2d | plasterer |  | 969.76 |  | 0
66 | ALCAYATA T-2 | 4.2.5 | 63FS |  | 2020-08-27 |  | 2d | mason |  | 507.76 |  | 0
67 | SEGURIDAD Y SALUD OCUPACIONAL | 4.3
68 | SEGURIDAD Y SALUD | 4.3.1 | 59FS |  | 2020-08-24 |  | 5d | team subcontractor |  | 1000 |  | 0
69 | MITIGACION AMBIENTAL | 4.4
70 | MITIGACION DE IMPACTO AMBIENTAL | 4.4.1 | 64FS |  | 2020-09-14 |  | 1d | team subcontractor |  | 1000 |  | 0
2020-10-12
55
|  |  | 0.13732 | 0.12259 | 1.6671 |  |  | 0.2449 | 0.42544 | 1.2233
|  |  | 0.13649 | 0.12122 | 1.729 |  |  | 0.36262 | 0.38541 | 0.93021
|  |  | 0.094166 | 0.0863 | 1.4653 |  |  | 0.064008 | 0.13421 | 2.2576
[8 empty] | 0.11941 | 0.12008 | 1.7036
|  |  | 13.732 | 12.2592 | 166.7102 |  |  | 0.11566 | 0.12142 | 1.6487
|  |  | 13.6487 | 12.1217 | 172.8975 |  |  | 0.098693 | 0.08147 | 0.97268
|  |  | 9.4166 | 8.63 | 146.5265
[8 empty] | 24.4898 | 42.5442 | 122.333
[8 empty] | 36.262 | 38.541 | 93.0214
| 0.25995 | 0.086212 | 3.6023 |  |  |  |  | 6.4008 | 13.4207 | 225.7564
| 0.25995 | 0.086212 | 3.6023 |  |  |  |  | 11.9407 | 12.0083 | 170.356
| 0.25995 | 0.086212 | 3.6023 |  |  |  |  | 11.5665 | 12.1421 | 164.8746
[8 empty] | 9.8693 | 8.147 | 97.2681
| 25.9946 | 8.6212 | 360.2271 |  |  |  |  | 0 | 0 | 0
| 25.9946 | 8.6212 | 360.2271
| 25.9946 | 8.6212 | 360.2271
|  | 2020-10-12 |  | 2020-10-12 17:00 |  | 2020-10-10 16:00 |  | 2020-10-13 17:00 |  | 2020-10-13 17:00 |  | 2020-10-13 17:00 |  | 2020-10-13 17:00 | 2020-10-13 17:00
| Planned duration | 2020-08-18
Real

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | electrician | Renewable | 5 people | 0 | 28
2 | team subcontractor | Renewable | 7 people | 0 | 26
3 | mason | Renewable | 2 people | 0 | 38
4 | carpenter | Renewable | 3 people | 0 | 26.8
5 | painter | Renewable | 6 people | 0 | 29
6 | plasterer | Renewable | 2 people | 0 | 39

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (hours) | Most probable (hours) | Pessimistic (hours)
0 | ACTIVIDADES GENERALES | [5 empty] | 942 | 952 | 961
2 | TRABAJOS PRELIMINARES | [5 empty] | 942 | 952 | 961
3 | MOVILIZACION Y DESMOVILIZACION DE MAQUINARIAS Y EQUIPOS |  | standard - symmetric | 50 | 100 | 150 | 44 | 56 | 67
4 | PUENTE CONIN | [5 empty] | 64 | 80 | 96
5 | OBRAS PRELIMINARES | [5 empty] | 198 | 200 | 202
6 | CARTEL DE OBRA |  | standard - symmetric | 50 | 100 | 150 | 594 | 600 | 606
7 | LIMPIEZA DEL TERRENO MANUAL |  | standard - no risk | 50 | 100 | 150 | 237 | 240 | 242
8 | ALMACEN Y GUARDIANIA |  | standard - skewed left | 33.3333 | 100 | 133.3333 | 192 | 264 | 288
9 | TRAZO Y REPLANTEO INICIAL |  | standard - no risk | 50 | 100 | 150 | 118 | 120 | 121
10 | ENCAUZAMIENTO DEL CAUCE DEL RIO |  | standard - no risk | 57.1429 | 100 | 142.8571 | 237 | 240 | 242
11 | SUBESTRUCTURA | [5 empty] | 118 | 120 | 121
12 | EXCAVACION PARA ESTRIBOS EN TERRENO NORMAL CON MAQUINARIA |  | standard - no risk | 40 | 100 | 160 | 118 | 120 | 121
13 | RELLENO COMPACTADO CON MATERIAL PROPIO |  | standard - no risk | 66.6667 | 100 | 133.3333 | 118 | 120 | 121
14 | ELIMINACION DE MATERIAL EXCEDENTE CON MAQUINARI, D=1.5 KM. |  | standard - no risk | 50 | 100 | 150 | 475 | 480 | 484
15 | ENCOFRADO Y DESENCOFRADO DE ESTRIBO |  | standard - no risk | 60 | 100 | 140 | 158 | 160 | 161
16 | CONCRETO f'c=175 kg/cm2 + 30% PM. |  | standard - no risk | 50 | 100 | 150 | 118 | 120 | 121
17 | PUENTE PROVISIONAL | [5 empty] | 118 | 120 | 121
18 | SUPERESTRUCTURA DE ROLLIZO (L=18.00 M.) |  | standard - no risk | 60 | 100 | 140 | 118 | 120 | 121
19 | CONSTRUCCION DE MADERAMEN |  | standard - no risk | 20 | 100 | 180 | 118 | 120 | 121
20 | ALCAYATAS T-1 |  | standard - no risk | 50 | 100 | 150 | 118 | 120 | 121
21 | ALCAYATAS T-2 |  | standard - no risk | 50 | 100 | 150 | 95 | 96 | 96
22 | DEFENSA RIBEREÑA | [5 empty] | 522 | 528 | 533
23 | EXCAVACION EN MATERIAL COMUN BAJO AGUA |  | standard - no risk | 33.3333 | 100 | 166.6667 | 158 | 160 | 161
24 | PERFILADO PARA BASE DE ESTRUCTURA |  | standard - no risk | 33.3333 | 100 | 166.6667 | 158 | 160 | 161
25 | RELLENO Y COMPACTADO PARA ESTRUCTURAS |  | standard - no risk | 33.3333 | 100 | 166.6667 | 118 | 120 | 121
26 | ELIMINACION DE MATERIAL EXCEDENTE A 100M. |  | standard - no risk | 50 | 100 | 150 | 118 | 120 | 121
27 | GEOTEXTIL NO TEJIDO TIPO I |  | standard - no risk | 50 | 100 | 150 | 79 | 80 | 80
28 | GAVIONES TIPO CAJA 5.0x1.0x2.0 |  | standard - no risk | 33.3333 | 100 | 166.6667 | 118 | 120 | 121
29 | GAVIONES TIPO CAJA 5.0x1.0x1.5 |  | standard - no risk | 71.4286 | 100 | 128.5714 | 118 | 120 | 121
30 | GAVIONES TIPO CAJA 5.0x1.0x1.0 |  | standard - no risk | 33.3333 | 100 | 166.6667 | 118 | 120 | 121
31 | GAVIONES TIPO COLCHON 5.0x2.0x0.30M. |  | standard - no risk | 50 | 100 | 150 | 118 | 120 | 121
32 | ENROCADO DE PROTECCION (AGUAS ARRIBA) | [5 empty] | 356 | 360 | 363
33 | EXTRACCION, SELECCIÓN Y ACOPIO DE ROCA |  | standard - no risk | 50 | 100 | 150 | 158 | 160 | 161
34 | CARGUIO Y TRANSPORTE DE ROCA (D=1KM) |  | standard - no risk | 50 | 100 | 150 | 118 | 120 | 121
35 | ACOMODADO DE ROCA EN LA UÑA |  | standard - no risk | 50 | 100 | 150 | 158 | 160 | 161
36 | ACOMODADO DE ROCA EN TALUD |  | standard - no risk | 50 | 100 | 150 | 118 | 120 | 121
37 | SEGURIDAD Y SALUD OCUPACIONAL | [5 empty] | 96 | 108 | 144
38 | SEGURIDAD Y SALUD |  | standard - skewed right | 60 | 100 | 160 | 96 | 108 | 144
39 | MITIGACION AMBIENTAL | [5 empty] | 96 | 132 | 144
40 | MITIGACION DE IMPACTO AMBIENTAL |  | standard - skewed left | 25 | 100 | 150 | 64 | 88 | 96
41 | PUENTE CHACPAR | [5 empty] | 118 | 120 | 121
42 | OBRAS PRELIMINARES | [5 empty] | 118 | 120 | 121
43 | CARTEL DE OBRA |  | standard - no risk | 50 | 100 | 150
44 | LIMPIEZA DEL TERRENO MANUAL |  | standard - skewed right | 66.6667 | 100 | 166.6667
45 | ALMACEN Y GUARDIANIA |  | standard - skewed right | 50 | 100 | 250
46 | REPARACION DE ESTRUCTURA
47 | ELIMINACION DE ROLLIZOS Y TABLONES |  | standard - skewed left | 25 | 100 | 150
48 | SUPERESTRUCTURA DE ROLLIZO (L=11.80 M.) |  | standard - no risk | 50 | 100 | 150
49 | CONSTRUCCION DE MADERAMEN |  | standard - no risk | 83.3333 | 100 | 116.6667
50 | ALCAYATA T-1 |  | standard - no risk | 50 | 100 | 150
51 | ALCAYATA T-2 |  | standard - no risk | 50 | 100 | 150
52 | SEGURIDAD Y SALUD OCUPACIONAL
53 | SEGURIDAD Y SALUD |  | standard - skewed left | 20 | 100 | 140
54 | MITIGACION AMBIENTAL
55 | MITIGACION DE IMPACTO AMBIENTAL |  | standard - skewed left | 25 | 100 | 150
56 | PUENTE LANCHAN
57 | OBRAS PRELIMINARES
58 | CARTEL DE OBRA |  | standard - no risk | 50 | 100 | 150
59 | LIMPIEZA DEL TERRENO MANUAL |  | standard - no risk | 50 | 100 | 150
60 | ALMACEN Y GUARDIANIA |  | standard - no risk | 50 | 100 | 150
61 | REPARACION DE ESTRUCTURA
62 | ELIMINACION DE ROLLIZOS Y TABLONES |  | standard - no risk | 50 | 100 | 150
63 | SUPERESTRUCTURA DE ROLLIZO (L=6.80 M.) |  | standard - no risk | 50 | 100 | 150
64 | CONSTRUCCION DE MADERAMEN |  | standard - no risk | 88.8889 | 100 | 111.1111
65 | ALCAYATA T-1 |  | standard - no risk | 50 | 100 | 150
66 | ALCAYATA T-2 |  | standard - no risk | 50 | 100 | 150
67 | SEGURIDAD Y SALUD OCUPACIONAL
68 | SEGURIDAD Y SALUD |  | standard - no risk | 40 | 100 | 160
69 | MITIGACION AMBIENTAL
70 | MITIGACION DE IMPACTO AMBIENTAL |  | standard - no risk | 50 | 100 | 150

## Project Control - TP1
| TP Status Date | 2020-10-14 08:00 |  | TP Name | Earthwork
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | ACTIVIDADES GENERALES
2 | TRABAJOS PRELIMINARES
3 | MOVILIZACION Y DESMOVILIZACION DE MAQUINARIAS Y EQUIPOS | [9 empty] | 2020-08-18 | 1d | [5 empty] | 16275 |  | 100%
4 | PUENTE CONIN
5 | OBRAS PRELIMINARES
6 | CARTEL DE OBRA | [9 empty] | 2020-08-19 | 1d | [5 empty] | 450 |  | 100%
7 | LIMPIEZA DEL TERRENO MANUAL | [9 empty] | 2020-08-19 | 3d | [5 empty] | 5779.8 |  | 100%
8 | ALMACEN Y GUARDIANIA | [9 empty] | 2020-08-21 | 3d | [5 empty] | 1200 |  | 100%
9 | TRAZO Y REPLANTEO INICIAL | [9 empty] | 2020-08-24 | 2d | [5 empty] | 988 |  | 100%
10 | ENCAUZAMIENTO DEL CAUCE DEL RIO | [9 empty] | 2020-08-18 | 6d | [5 empty] | 11243.6 |  | 100%
11 | SUBESTRUCTURA
12 | EXCAVACION PARA ESTRIBOS EN TERRENO NORMAL CON MAQUINARIA | [9 empty] | 2020-08-25 | 4d | [5 empty] | 5325.2 |  | 100%
13 | RELLENO COMPACTADO CON MATERIAL PROPIO | [9 empty] | 2020-08-30 | 10d | [5 empty] | 4105.52 |  | 100%
14 | ELIMINACION DE MATERIAL EXCEDENTE CON MAQUINARI, D=1.5 KM. | [9 empty] | 2020-09-05 | 2d | [5 empty] | 9586.82 |  | 100%
15 | ENCOFRADO Y DESENCOFRADO DE ESTRIBO | [9 empty] | 2020-09-07 | 5d | [5 empty] | 5522.06 |  | 100%
16 | CONCRETO f'c=175 kg/cm2 + 30% PM. | [9 empty] | 2020-09-12 | 12d | [5 empty] | 59414.72 |  | 100%
17 | PUENTE PROVISIONAL
18 | SUPERESTRUCTURA DE ROLLIZO (L=18.00 M.) | [9 empty] | 2020-09-22 | 6d | [5 empty] | 4304.28 |  | 100%
19 | CONSTRUCCION DE MADERAMEN | [9 empty] | 2020-09-27 | 2d | [5 empty] | 20411.64 |  | 100%
20 | ALCAYATAS T-1 | [9 empty] | 2020-09-27 | 3d | [5 empty] | 2556.64 |  | 100%
21 | ALCAYATAS T-2 | [9 empty] | 2020-10-02 | 4d | [5 empty] | 1384.8 |  | 100%
22 | DEFENSA RIBEREÑA
23 | EXCAVACION EN MATERIAL COMUN BAJO AGUA | [9 empty] | 2020-09-22 | 4d | [5 empty] | 2022.24 |  | 100%
24 | PERFILADO PARA BASE DE ESTRUCTURA | [9 empty] | 2020-09-25 | 4d | [5 empty] | 835.65 |  | 100%
25 | RELLENO Y COMPACTADO PARA ESTRUCTURAS | [9 empty] | 2020-09-28 | 5d | [5 empty] | 1278.72 |  | 100%
26 | ELIMINACION DE MATERIAL EXCEDENTE A 100M. | [9 empty] | 2020-10-01 | 2d | [5 empty] | 1229.56 |  | 100%
27 | GEOTEXTIL NO TEJIDO TIPO I | [9 empty] | 2020-10-02 | 1d | [5 empty] | 260.46 |  | 100%
28 | GAVIONES TIPO CAJA 5.0x1.0x2.0 | [9 empty] | 2020-10-02 | 3d | [5 empty] | 10008.6 |  | 100%
29 | GAVIONES TIPO CAJA 5.0x1.0x1.5 | [9 empty] | 2020-10-05 | 1d | [5 empty] | 23678.33 |  | 100%
30 | GAVIONES TIPO CAJA 5.0x1.0x1.0 | [9 empty] | 2020-10-05 | 5d | [5 empty] | 5616.45 |  | 100%
31 | GAVIONES TIPO COLCHON 5.0x2.0x0.30M. | [9 empty] | 2020-10-05 | 2d | [5 empty] | 3925.8 |  | 100%
32 | ENROCADO DE PROTECCION (AGUAS ARRIBA)
33 | EXTRACCION, SELECCIÓN Y ACOPIO DE ROCA | [9 empty] | 2020-10-02 | 2d | [5 empty] | 274.8 |  | 100%
34 | CARGUIO Y TRANSPORTE DE ROCA (D=1KM) | [9 empty] | 2020-10-04 | 3d | [5 empty] | 375.6 |  | 100%
35 | ACOMODADO DE ROCA EN LA UÑA | [9 empty] | 2020-10-06 | 2d | [5 empty] | 81.45 |  | 100%
36 | ACOMODADO DE ROCA EN TALUD | [9 empty] | 2020-10-06 | 2d | [5 empty] | 244.13 |  | 100%
37 | SEGURIDAD Y SALUD OCUPACIONAL
38 | SEGURIDAD Y SALUD | [9 empty] | 2020-08-21 | 2d | [5 empty] | 1000 |  | 100%
39 | MITIGACION AMBIENTAL
40 | MITIGACION DE IMPACTO AMBIENTAL | [9 empty] | 2020-10-12 | 2d | [5 empty] | 1000 |  | 100%
41 | PUENTE CHACPAR
42 | OBRAS PRELIMINARES
43 | CARTEL DE OBRA | [9 empty] | 2020-08-19 | 1d | [5 empty] | 450 |  | 100%
44 | LIMPIEZA DEL TERRENO MANUAL | [9 empty] | 2020-08-20 | 6d | [5 empty] | 2808 |  | 100%
45 | ALMACEN Y GUARDIANIA | [9 empty] | 2020-08-26 | 1d | [5 empty] | 1200 |  | 100%
46 | REPARACION DE ESTRUCTURA
47 | ELIMINACION DE ROLLIZOS Y TABLONES | [9 empty] | 2020-08-27 | 1d | [5 empty] | 743.15 |  | 100%
48 | SUPERESTRUCTURA DE ROLLIZO (L=11.80 M.) | [9 empty] | 2020-08-28 | 1d | [5 empty] | 4124.28 |  | 100%
49 | CONSTRUCCION DE MADERAMEN | [9 empty] | 2020-08-29 | 24d | [5 empty] | 13582.28 |  | 100%
50 | ALCAYATA T-1 | [9 empty] | 2020-08-29 | 4d | [5 empty] | 1719.12 |  | 100%
51 | ALCAYATA T-2 | [9 empty] | 2020-08-29 | 2d | [5 empty] | 900.12 |  | 100%
52 | SEGURIDAD Y SALUD OCUPACIONAL
53 | SEGURIDAD Y SALUD | [9 empty] | 2020-08-26 | 5d | [5 empty] | 1000 |  | 100%
54 | MITIGACION AMBIENTAL
55 | MITIGACION DE IMPACTO AMBIENTAL | [9 empty] | 2020-09-22 | 1d | [5 empty] | 1000 |  | 100%
56 | PUENTE LANCHAN
57 | OBRAS PRELIMINARES
58 | CARTEL DE OBRA | [9 empty] | 2020-08-19 | 1d | [5 empty] | 450 |  | 100%
59 | LIMPIEZA DEL TERRENO MANUAL | [9 empty] | 2020-08-20 | 4d | [5 empty] | 1872 |  | 100%
60 | ALMACEN Y GUARDIANIA | [9 empty] | 2020-08-24 | 1d | [5 empty] | 1200 |  | 100%
61 | REPARACION DE ESTRUCTURA
62 | ELIMINACION DE ROLLIZOS Y TABLONES | [9 empty] | 2020-08-25 | 1d | [5 empty] | 743.15 |  | 100%
63 | SUPERESTRUCTURA DE ROLLIZO (L=6.80 M.) | [9 empty] | 2020-08-26 | 1d | [5 empty] | 4004.28 |  | 100%
64 | CONSTRUCCION DE MADERAMEN | [9 empty] | 2020-08-27 | 18d | [5 empty] | 7625.16 |  | 100%
65 | ALCAYATA T-1 | [9 empty] | 2020-08-27 | 2d | [5 empty] | 969.76 |  | 100%
66 | ALCAYATA T-2 | [9 empty] | 2020-08-27 | 2d | [5 empty] | 507.76 |  | 100%
67 | SEGURIDAD Y SALUD OCUPACIONAL
68 | SEGURIDAD Y SALUD | [9 empty] | 2020-08-24 | 5d | [5 empty] | 1000 |  | 100%
69 | MITIGACION AMBIENTAL
70 | MITIGACION DE IMPACTO AMBIENTAL | [9 empty] | 2020-09-14 | 1d | [5 empty] | 1000 |  | 100%

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2026-01-01
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | Yes
6:00 - 7:00 | No | Sunday | Yes
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3